Marine Champion Action Day Checklist

1. Planning the event (at least one month before the day)

| ☐ | Decide the type of event (e.g. underwater litter pick, beach clean, oyster survey, seagrass survey). |
| --- | --- |
| ☐ | Choose a suitable location and date based on your club’s diving/snorkelling abilities and travel options. |
| ☐ | Discuss the event with: - ☐ Club Diving Officer - ☐ Club committee - ☐ Event organisers within the club |
| ☐ | Confirm who will lead the diving activities (Marine Champions support organisation but do not lead dives – unless of appropriate qualification). |
| ☐ | Confirm appointed Dive/Shore Manager and Assistants (Dive Managers should be Dive Leader or above – appropriate to the site/activity) |
| ☐ | Check BSAC guidance and resources for safety and event planning. |
| ☐ | Complete a risk assessment (risk assessment should be conducted with support/approval of a Dive Leader or above). |
| ☐ | At least one month before event date register your event with BSAC using the event registration form and attach your risk assessment for approval. https://www.bsac.com/forms/marine-champion-action-day-submission-form/ |
|  | The period of registration is necessary to allow time for: |
|  | - Potential iterative discussion with HQ advisors - Revision of proposed Risk Assessment - Provision of approval in time to finalise plans for the event |

2. Planning the event (once activity has confirmed approval from BSAC HQ)

| ☐ | Arrange required equipment, e.g.: - ☐ Gloves - ☐ Collection bags / containers - ☐ Data recording sheets - ☐ Cameras or phones for documentation - ☐ First aid kit - ☐ O2 set |
| --- | --- |
| ☐ | Identify helpers/volunteers within the club to support the event. |
| ☐ | Promote the event and get participants to register (event registration link will be provided by BSAC once event approved ): - ☐ Club WhatsApp / Facebook group - ☐ Email members - ☐ Club noticeboard - ☐ Invite families or non-divers if appropriate |
| ☐ | Confirm logistics - ☐ Meeting point - ☐ Start and finish time - ☐ Parking/access - ☐ Waste disposal plan |

3. On the Day

Briefing

| ☐ | Welcome participants |
| --- | --- |
| ☐ | Site and SEEDS brief including: - ☐ Purpose of the event - ☐ Safety considerations - ☐ What data will be recorded |
| ☐ | Confirm roles: - ☐ Dive Manager / Shore Manager - ☐ Dive leader / snorkel lead - ☐ Shore support - ☐ Data recorder |
| ☐ | Remind everyone about: - ☐ Environmental responsibility - ☐ Safe lifting of debris |

Activity

| ☐ | Conduct dive / beach clean / survey |
| --- | --- |
| ☐ | Ensure participants follow safety guidance |
| ☐ | Collect: - ☐ Litter or debris - ☐ Survey data (e.g. oysters, seagrass) |
| ☐ | Take photos or video of the activity |
| ☐ | Record: - ☐ Number of participants - ☐ Amount/type of litter - ☐ Wildlife sightings |

4. After the event

| ☐ | Ensure waste is disposed of correctly |
| --- | --- |
| ☐ | Thank all participants |
| ☐ | Compile the event results: - ☐ Number of participants - ☐ Items collected - ☐ Survey findings |
| ☐ | Submit any citizen science data (e.g. Operation Oyster forms). |
| ☐ | Share results: - ☐ Club social media - ☐ Tag BSAC and relevant hashtags - ☐ Club website/newsletter |
| ☐ | Upload photos and updates to BSAC Marine Champions team using upload link provided for your event (issued once risk assessment approved). |
| ☐ | Record feedback to improve future events. |